## Project Inputs
Burndown Chart
kickoff.pmi.org | Project Name: | Cloud Kitchen
| Project Manager: | Ameer Hamza
SPRINT 3
How To Use This Worksheet:
Objective | This is a template that can be used to create a burndown chart. This specific template assumes a five day sprint.
What To Complete | All fields where cells are shaded gray. In these cells, first enter the total number of hours needed to complete each task; then, enter the number of hours spent daily on each of the tasks. Do not enter any values in white cells.
Content Requirements | Name | Description
| Actual Effort | This tracks the actual number of hours remaining for the collective tasks in a sprint. This is estimated on a daily basis.
| Ideal Effort | This tracks the ideal/projected number of hours remaining for the collective tasks in a sprint. This is estimated on a daily basis.
| Starting Hours | This indicates the number of hours needed to complete a task before any work is done.
| Task | This indicates the name/title of each task that is being tracked.
| Day | This is the number of hours spent on a given task for the day.
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
Actual Effort (Hours) | 111 | 92 | 68 | 44 | 10 | 0
Ideal Effort (Hours) | 111 | 88.8 | 66.6 | 44.4 | 22.2 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Total
Create a frontend for chef to change order status and add delivery fee. | 3 | 3 |  |  |  |  | 3
Backend API for chef to change order status to "On the way". | 5 | 5 |  |  |  |  | 5
Develop Backend API for chef to set a delivery fee for rider. | 5 | 5 |  |  |  |  | 5
Integerate Both frontend and backend APIs. | 3 |  | 3 |  |  |  | 3
Create a FrontEnd Page for riders to see and accept/reject the order. | 3 | 3 |  |  |  |  | 3
Develop Backend APIs for accepting/rejecting the order | 8 |  | 8 |  |  |  | 8
Crerate FrontEnd Where chef can recive update by rider. | 3 | 3 |  |  |  |  | 3
Develop BackEnd API for storing udpate by rider in database. | 5 |  | 5 |  |  |  | 5
Integerate all frontend and backend APIs. | 5 |  | 5 |  |  |  | 5
Make a frontend Page where rider can udpdate order status. | 5 |  | 3 | 2 |  |  | 5
Develop Backend API for storing udpated status and informing the customer. | 8 |  |  | 8 |  |  | 8
Integerate FrontEnd and Backend APIs. | 3 |  |  |  | 3 |  | 3
Develop frontend Page for showing "On the way" orders to the riders. | 5 |  |  | 5 |  |  | 5
Develop Backend API for fetching "On the way" orders from the database. | 5 |  |  | 3 | 2 |  | 5
Integerate Frontend with Backend. | 3 |  |  | 3 |  |  | 3
Create FrontEnd for user reviewing Page. | 5 |  |  |  | 5 |  | 5
Develop Backend API for customer reviewing Page. | 8 |  |  |  | 8 |  | 8
Integerate FrontEnd and Backend APIs. | 3 | [5 empty] | 0
Develop FrontEnd page for admin reviewing the Kitchen. | 5 |  |  |  | 5 |  | 5
Create FrontEnd for admin to remove the kitchen. | 3 |  |  |  | 3 |  | 3
Develop Backend Api for admin to see all the reviews. | 8 |  |  |  | 8 |  | 8
Integerate all the frontend and backend APIs. | 5 |  |  |  |  | 5 | 5
Develop Backend Api for admin to remove the kichen. | 5 |  |  |  |  | 5 | 5