## Project Inputs
Burndown Chart
kickoff.pmi.org | Project Name: | Cloud Kitchen
| Project Manager: | Dr. Syed Khaldoon Khurshid
SPRINT 2
How To Use This Worksheet:
Objective | This is a template that can be used to create a burndown chart. This specific template assumes a five day sprint.
What To Complete | All fields where cells are shaded gray. In these cells, first enter the total number of hours needed to complete each task; then, enter the number of hours spent daily on each of the tasks. Do not enter any values in white cells.
Content Requirements | Name | Description
| Actual Effort | This tracks the actual number of hours remaining for the collective tasks in a sprint. This is estimated on a daily basis.
| Ideal Effort | This tracks the ideal/projected number of hours remaining for the collective tasks in a sprint. This is estimated on a daily basis.
| Starting Hours | This indicates the number of hours needed to complete a task before any work is done.
| Task | This indicates the name/title of each task that is being tracked.
| Day | This is the number of hours spent on a given task for the day. | [10 empty] | Velocity Chart Data
| Story Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Actual Effort (Story Points) | 148 | 127 | 108 | 89 | 68 | 52 | 39 | 26 | 17 | 13 | 5 |  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Ideal Effort (Story Points) | 148 | 133.2 | 118.4 | 103.6 | 88.8 | 74 | 59.2 | 44.4 | 29.6 | 14.8 | 0 |  | Actual Effort (Story Points) | 21 | 19 | 19 | 21 | 16 | 13 | 13 | 9 | 4 | 8 | 143
[13 empty] | Ideal Effort (Story Points) | 21 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 154.2
Tasks | Story Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total | Average | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8
Develop frontEnd Daily Meal Menu Uploading System | 5 | Day 1: 5 | 5
Develope a Menu Histroy Page showing Past Menu of the respective dates | 3 | Day 1: 3 | 3
Develop Backend APi for Daily Menu uploading | 8 | Day 1: 5; Day 2: 3 | 8
Integerate FrontEnd With backend | 3 | Day 2: 3 | 3
Develope Backend For Save Menu in Menu History Page. | 8 | Day 1: 8 | 8
Design a Page for Exploring Kitchen & Menu | 3 | Day 2: 3 | 3
Convert Design In Code i.e. make frontend of kitchen menu | 5 | Day 2: 5 | 5
Develop Frontend interactive session for customer and chef | 5 | Day 2: 2; Day 3: 3 | 5
Develop Backend API for fetching all the kitchens & their menu from database | 8 | Day 2: 3; Day 3: 5; Day 4: 2 | 10
Develop API for customer & chef interaction | 13 | Day 7: 3; Day 8: 5 | 8
Integrate Backend with Frontend | 3 | Day 3: 3 | 3 | Day | Sprint 1 Actual | Sprint 1 Ideal | Sprint 2 Actual | Sprint 2 Ideal
Design a page for placing customized Meal Order | 2 | Day 3: 2 | 2 | Day 1 | 21 | 21 | 8 | 8
Convert customization page design into proper frontend where customer can place order according to their choice | 3 | Day 3: 3 | 3 | Day 2 | 19 | 18.6 | 21 | 18.6
Develop Backend API for food customization page according to the frontend implemented | 5 | Day 3: 3; Day 4: 2 | 5 | Day 3 | 19 | 16.2 | 11 | 16.2
Add "Save Preferences" button & store user choices for future orders | 5 | Day 4: 3 | 3 | Day 4 | 21 | 13.8 | 12 | 13.8
Integrate Frontend & Backend | 3 | Day 4: 3 | 3 | Day 5 | 16 | 11.4 | 23 | 11.4
Design a Cart Page where all the items in cart will be visible | 3 | Day 4: 3 | 3 | Day 6 | 13 | 9 | 23 | 9 |  |  | Sprint | Ideal Effort | Actual Effort
Implement Frontend of Cart Page according to the design & develop payment page | 5 | Day 4: 3; Day 5: 2 | 5 | Day 7 | 13 | 6.6 | 17 | 6.6 |  |  | Sprint 1 | 147 | 152
Develop Backend API for implementing add to cart functionality & cart page according to the frontend designed | 8 | Day 4: 5; Day 5: 3 | 8 | Day 8 | 9 | 4.2 | 18 | 4.2 |  |  | Sprint 2 | 150.2 | 146
Integrate frontend and backend of this page | 3 | Day 5: 3 | 3 | Day 9 | 4 | 1.8 | 11 | 1.8 |  |  | Sprint 3 | 131 | 139
Implement FrontEnd of Checkout Page for placing order for selected items from the cart or customized meals. | 3 | Day 5: 3 | 3 | Day 10 | 8 | 0 | 8 | 0
Integerate a third party payment system (Stripe) for online Payments. | 5 | Day 5: 3; Day 6: 2 | 5 |  | 143 | 102.6
Develop Backend APi for order placement and updating the database. | 5 | Day 5: 2; Day 6: 3 | 5
Integertae backend & Frontend for order placement. | 3 | Day 6: 3 | 3
Deisgn a page where chef can review the customized orders he/she has received. | 2 | Day 6: 2 | 2
Convert the design in code for reviewing customized orders. (Make frontend) | 3 | Day 6: 3 | 3
Develop Backend APi for chef reviewing the customized orders. | 5 | Day 7: 5 | 5
Integerate FrontEnd with Backend so make things work out for chef and customer. | 3 | Day 7: 3 | 3
Implement FrontEnd of a page for chef to review regular orders. | 3 | Day 7: 2; Day 8: 1 | 3
Develop Backend API for order reviewing page. | 5 | Day 8: 3; Day 9: 2 | 5
Integerate FrontEnd and Backend. | 2 | Day 9: 2 | 2
Documentation: Sprint Schedule Document, Retrospective Document, Sprint Review Document. | 8 | Day 10: 8 | 8
143