## Project Inputs
Burndown Chart
kickoff.pmi.org | Project Name: | Cloud Kitchen
| Project Manager: | Dr.Khaldoon Khurshid.
SPRINT 1
How To Use This Worksheet:
Objective | This is a template that can be used to create a burndown chart. This specific template assumes a five day sprint.
What To Complete | All fields where cells are shaded gray. In these cells, first enter the total number of hours needed to complete each task; then, enter the number of hours spent daily on each of the tasks. Do not enter any values in white cells.
Content Requirements | Name | Description
| Actual Effort | This tracks the actual number of hours remaining for the collective tasks in a sprint. This is estimated on a daily basis.
| Ideal Effort | This tracks the ideal/projected number of hours remaining for the collective tasks in a sprint. This is estimated on a daily basis.
| Starting Hours | This indicates the number of hours needed to complete a task before any work is done.
| Task | This indicates the name/title of each task that is being tracked.
| Day | This is the number of hours spent on a given task for the day.
| Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Actual Effort (Hours) | 157 | 149 | 127 | 116 | 100 | 80 | 56 | 42 | 21 | 14 | 0
Ideal Effort (Hours) | 157 | 141.3 | 125.6 | 109.9 | 94.2 | 78.5 | 62.8 | 47.1 | 31.4 | 15.7 | 0
Tasks | Starting Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Story Points | Total
UI: Homepage Designing | 4 | Day 1: 4 | 3 | 4
Frontend: Develop Homepage FrontEnd | 4 | Day 1: 4 | 5 | 4
UI: Design Customer Registration UI | 4 | Day 1: 0; Day 2: 4 | 2 | 4
Frontend: Implement Customer Registration FrontEnd | 5 | Day 1: 0; Day 2: 5 | 5 | 5
Implement Email & Phone Number validation. | 3 | Day 1: 0; Day 2: 3 | 3 | 3
Backend: Develop Customer Registration Backend API. | 5 | Day 1: 0; Day 2: 5 | 8 | 5
Integration: Integerate Customer Registration Frontend/Backend | 5 | Day 1: 0; Day 2: 5 | 3 | 5
UI: Design Chef's Kitchen Registeration UI | 5 | Day 1: 0; Day 2: 0; Day 3: 5 | 3 | 5
Frontend: Create Chef's Kitchen Registeration Frontend | 4 | Day 1: 0; Day 2: 0; Day 3: 4 | 5 | 4
Backend: Implement Chef's Kitchen Registeration backend API. | 6 | Day 1: 0; Day 2: 0; Day 3: 2; Day 4: 4 | 8 | 6
Verification: Secure Chef's Kitchen registration after admin's approval. | 2 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 2 | 2 | 2
Integeration: Integerate Frontend, Backend Chef's Kitchen Registeration APIs. | 4 | Day 3: 0; Day 4: 4 | 3 | 4
UI: Design Delivery Partner Registration UI/UX. | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 2; Day 5: 2 | 2 | 4
Frontend: Develop Delivery Partner Registration Frontend. | 4 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 4 | 5 | 4
Backend: Create Delivery Partner Registration Backend APIs. | 5 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 5 | 8 | 5
Verification: Implement verification process for delivery partners (Integrate identity verification (CNIC, license upload)) | 2 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0 | 3 | 0
Integration: Implement Delivery Partner Registration integeration. | 5 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 5 | 3 | 5
UI: Desgin Chef Profile & DashBoard UI/UX. | 6 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 4; Day 5: 2 | 5 | 6
Frontend: Develop Chef Profile & DashBoard Frontend. | 4 | 0 | 0 | 0 | 0 | 2 | 3 |  |  |  |  | 5 | 5
Backend: Create Chef Profile & DashBoard Backend APIs. | 6 | 0 | 0 | 0 | 0 | 0 | 6 |  |  |  |  | 8 | 6
Integration: Implement Chef Profile & DashBoard Integerations. | 4 | 0 | 0 | 0 | 0 | 0 | 4 |  |  |  |  | 3 | 4
UI: Design Admin Panel Design UI/UX. | 5 | 0 | 0 | 0 | 0 | 0 | 5 |  |  |  |  | 3 | 5
Frontend: Create Frontend of Admin Panel. | 5 | 0 | 0 | 0 | 0 | 0 | 5 |  |  |  |  | 5 | 5
Backend: Implement Backend Admin Panel API. | 6 | Day 5: 0; Day 6: 1; Day 7: 5 | 8 | 6
Integration: Integeration of Admin Panel Backend, Frontend APIs. | 5 | Day 6: 0; Day 7: 2; Day 8: 3 | 3 | 5
UI: Design Customer Profile & DashBoard UI | 5 | Day 5: 0; Day 7: 5 | 2 | 5
Frontend: Develop Customer Profile & DashBoard Frontend | 5 | Day 7: 2; Day 8: 3 | 5 | 5
Backend: Create Customer Profile & DashBoard Backend API. | 6 | Day 6: 0; Day 7: 0; Day 8: 6 | 8 | 6
Integration: Integerate Backend and frontend Customer Profile & DashBoard APIs. | 5 | Day 7: 0; Day 8: 2; Day 9: 4 | 3 | 6
UI: Design Delivery Partner Profile & DashBoard UI/UX | 4 | Day 7: 0; Day 8: 4 | 2 | 4
Frontend: Develop Delivery Partner Profile & DashBoard Frontend. | 5 | Day 8: 3; Day 9: 2 | 5 | 5
Backend: Implement Delivery Partner Profile & DashBoard Backend APIs. | 6 | Day 9: 1; Day 10: 5 | 8 | 6
Integration: Integerate Delivery Partner Profile & DashBoard Frontend & Backend APIs. | 4 | Day 9: 0; Day 10: 4 | 3 | 4
Docuemntation: Sprint Schedule Document, Retrospective Document, Sprint Review Document. | 5 | Day 9: 0; Day 10: 5 | 8 | 5