## Project Inputs
Burndown Chart
kickoff.pmi.org | Project Name: | Cloud Kitchen
| Project Manager: | Dr. Syed Khaldoon Khurshid
SPRINT 1
How To Use This Worksheet:
Objective | This is a template that can be used to create a burndown chart. This specific template assumes a five day sprint.
What To Complete | All fields where cells are shaded gray. In these cells, first enter the total number of hours needed to complete each task; then, enter the number of hours spent daily on each of the tasks. Do not enter any values in white cells.
Content Requirements | Name | Description
| Actual Effort | This tracks the actual number of hours remaining for the collective tasks in a sprint. This is estimated on a daily basis.
| Ideal Effort | This tracks the ideal/projected number of hours remaining for the collective tasks in a sprint. This is estimated on a daily basis.
| Starting Hours | This indicates the number of hours needed to complete a task before any work is done.
| Task | This indicates the name/title of each task that is being tracked.
| Day | This is the number of hours spent on a given task for the day. | [10 empty] | Velocity Chart Data
| Story Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Actual Effort (Story Points) | 155 | 147 | 126 | 115 | 103 | 80 | 57 | 40 | 22 | 11 | 3 |  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
Ideal Effort (Story Points) | 155 | 139.5 | 124 | 108.5 | 93 | 77.5 | 62 | 46.5 | 31 | 15.5 | 0 |  | Actual Effort (Story Points) | 8 | 21 | 11 | 12 | 23 | 23 | 17 | 18 | 11 | 8
[13 empty] | Ideal Effort (Story Points) | 8 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5
Tasks | Story Points | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Total | Average | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5 | 15.5
UI: Homepage Designing | 3 | Day 1: 3 | 3
Frontend: Develop Homepage FrontEnd | 5 | Day 1: 5 | 5
UI: Design Customer Registration UI | 2 | Day 2: 2 | 2
Frontend: Implement Customer Registration FrontEnd | 5 | Day 2: 5 | 5
Implement Email & Phone Number validation. | 3 | Day 2: 3 | 3
Backend: Develop Customer Registration Backend API. | 8 | Day 2: 8 | 8
Integration: Integerate Customer Registration Frontend/Backend | 3 | Day 2: 3 | 3
UI: Design Chef's Kitchen Registeration UI | 3 | Day 3: 3 | 3
Frontend: Create Chef's Kitchen Registeration Frontend | 5 | Day 3: 5 | 5
Backend: Implement Chef's Kitchen Registeration backend API. | 8 | Day 3: 3; Day 4: 5 | 8
Verification: Secure Chef's Kitchen registration after admin's approval. | 2 | Day 4: 2 | 2
Integeration: Integerate Frontend, Backend Chef's Kitchen Registeration APIs. | 3 | Day 4: 3 | 3
UI: Design Delivery Partner Registration UI/UX. | 2 | Day 4: 2 | 2
Frontend: Develop Delivery Partner Registration Frontend. | 5 | Day 5: 5 | 5
Backend: Create Delivery Partner Registration Backend APIs. | 8 | Day 5: 8 | 8
Verification: Implement verification process for delivery partners (Integrate identity verification (CNIC, license upload)) | 3 | Day 5: 0 | 0
Integration: Implement Delivery Partner Registration integeration. | 3 | Day 5: 3 | 3
UI: Desgin Chef Profile & DashBoard UI/UX. | 5 | Day 5: 5 | 5
Frontend: Develop Chef Profile & DashBoard Frontend. | 5 | Day 5: 2; Day 6: 3 | 5
Backend: Create Chef Profile & DashBoard Backend APIs. | 8 | Day 6: 8 | 8
Integration: Implement Chef Profile & DashBoard Integerations. | 3 | Day 6: 3 | 3
UI: Design Admin Panel Design UI/UX. | 3 | Day 6: 3 | 3
Frontend: Create Frontend of Admin Panel. | 5 | Day 6: 5 | 5
Backend: Implement Backend Admin Panel API. | 8 | Day 6: 1; Day 7: 7 | 8
Integration: Integeration of Admin Panel Backend, Frontend APIs. | 3 | Day 7: 3 | 3
UI: Design Customer Profile & DashBoard UI | 2 | Day 7: 2 | 2
Frontend: Develop Customer Profile & DashBoard Frontend | 5 | Day 7: 5 | 5
Backend: Create Customer Profile & DashBoard Backend API. | 8 | Day 8: 8 | 8
Integration: Integerate Backend and frontend Customer Profile & DashBoard APIs. | 3 | Day 8: 3 | 3
UI: Design Delivery Partner Profile & DashBoard UI/UX | 2 | Day 8: 2 | 2
Frontend: Develop Delivery Partner Profile & DashBoard Frontend. | 5 | Day 8: 5 | 5
Backend: Implement Delivery Partner Profile & DashBoard Backend APIs. | 8 | Day 9: 8 | 8
Integration: Integerate Delivery Partner Profile & DashBoard Frontend & Backend APIs. | 3 | Day 9: 3 | 3
Docuemntation: Sprint Schedule Document, Retrospective Document, Sprint Review Document. | 8 | Day 10: 8 | 8
152